## Gap Analysis
Gap Analysis — ShopNest Inc. ¦ Oracle Fusion Cloud SCM Implementation
Inventory & Procurement Module ¦ Prepared for: ShopNest Inc. ¦ Date: March 2026
Area | AS-IS (Current State) | TO-BE (Oracle Fusion) | Oracle Module | Priority | Est. Benefit
INVENTORY MANAGEMENT
Inventory visibility | Manual spreadsheets per warehouse. No real-time view across NY, CHI, LA. | Single real-time dashboard showing stock across all 3 warehouses. | Oracle Inventory Mgmt | High | Eliminate ~8 hrs/week manual updates
Reorder automation | Manual reorder decisions. Frequent stockouts and overstocking. | Automated reorder point triggers. Purchase requisition auto-created on breach. | Oracle Inventory Mgmt | High | Reduce stockouts by est. 60%
PROCUREMENT
Purchase orders | POs raised manually via email. No standard template or audit trail. | Structured PO creation with approval workflow and full audit log. | Oracle Purchasing | High | Full compliance & audit trail
Supplier management | No central supplier database. Duplicate vendors. No performance tracking. | Centralized supplier registry with scorecards and portal access. | Oracle Supplier Portal | Medium | Reduce duplicate vendors by 100%
FINANCE & COMPLIANCE
Invoice matching | Manual invoice verification. Errors cause overpayments or delays. | Automated 3-way match (PO + GRN + Invoice). Exceptions flagged only. | Oracle Payables | Medium | Reduce payment errors by est. 80%
Reporting & analytics | Ad-hoc Excel reports. No standard KPIs or procurement dashboards. | Pre-built SCM dashboards. Procurement spend analytics via Oracle OAC. | Oracle OAC | Low | Real-time exec visibility

## Implementation Plan
Oracle Fusion SCM — 6-Month Implementation Plan ¦ ShopNest Inc.
Phased rollout across 3 warehouses: New York ¦ Chicago ¦ Los Angeles
Phase | Duration | Scope | Oracle Modules | Success Criteria
Phase 1 Foundation | Months 1–2 | • Real-time inventory across 3 warehouses • Automated reorder point triggers • Structured PO creation & approval workflow • User training — warehouse & procurement teams | • Oracle Inventory Management • Oracle Purchasing • Oracle Approvals Management | • Live inventory dashboard operational • Zero manual POs via email • Reorder automation active for top 100 SKUs
Phase 2 Procurement | Months 3–4 | • Supplier portal go-live • Centralized vendor registry (deduplicated) • Automated 3-way match (PO+GRN+Invoice) • AP payment automation | • Oracle Supplier Portal • Oracle Payables • Oracle AP Automation | • All suppliers onboarded to portal • 3-way match auto-processing >90% invoices • Payment error rate <2%
Phase 3 Analytics | Months 5–6 | • Procurement spend dashboards • KPI reporting (fill rate, PO cycle time, supplier OTD) • Management reporting templates • Post-go-live optimization & UAT sign-off | • Oracle Analytics Cloud (OAC) • Oracle SCM Reporting • Oracle BI Publisher | • Executive dashboard live • All KPIs tracked & baselined • Full UAT sign-off completed

## KPI Tracker
ShopNest Inc. — ERP KPI Tracker (Post-Implementation)
KPI | Baseline (AS-IS) | Target (TO-BE) | Month 3 Actual | Month 6 Actual | Status
Stockout rate | 12% | <5% | 7% | 4% | On Track
PO processing time | 5 days | <1 day | 2 days | 0.5 days | On Track
Invoice match rate (auto) | 0% | >90% | 65% | 93% | On Track
Duplicate supplier records | 34 | 0 | 8 | 0 | Achieved
Inventory accuracy | 72% | >98% | 89% | 99% | Achieved
Procurement cost reduction | 0% | 18–24% | 9% | 21% | On Track